## P0 Project overview
↑ | 2026 Sustainability Report
P0. Project overview
1. Purpose
| This workbook | Single working file for SR26 data collection and project delivery: requirements, requests, responses, scoring, evidence, plus project plan, timeline, comms/web to-do list and content-contributor checklist (P-tabs).
| SR26 in one line | Transition-year report covering CY2026: distinguish activity under the former Sustainability Plan 2030 from foundations and early actions after the Sustainability 2030 launch (~20 Oct 2026 TBC). No published traffic lights in 2026.
2. Lessons from SR25 and actions for SR26
| Keep tailored data requests | SR25 streamlined requests achieved a 100% response rate → keep targeted, faculty-specific requests (see Request wording log); avoid complex requests.
| Keep independent senior review | Retain Target Status Review Group as the Sustainability Reporting Review Group (~15 Feb 2027).
| Strengthen data controls | Central Evidence register, data owner confirmation (columns Q–R on every request), data source records, Databook alignment.
| Integrate with Annual Report | Engage Annual Report team in October; shared dependency map; late operational data (Feb–Mar) on a later pathway.
| Agree comms roles early | RASCI with Strategic Communications, comms, digital and design at project start (P2).
| Plan web and close from the outset | Year-specific report URL, central landing page, analytics measures agreed before launch, formal retrospective (P3, P2).
| Simpler project management | This simplified tracker; induction walkthrough; direct messages for assigned tasks, group channel for shared updates; blocker escalation as a standing meeting item.
| Follow up non-approval | SR25: FBE filled in the template but did not approve; Science disagreed with metrics → track 'Owner confirmed' in the Request tracker and chase; offer January support meetings.
3. How to use this workbook
| Records management | Save on the Sustainability Strategy Team SharePoint (Sustainability report 2026 > Report development). One document owner per working file; notify collaborators when a new version is saved. Avoid extra sub-folders in the data folder.
| Responses | Paste returned responses into the Faculties / central-unit tabs without inserting rows inside a block (A1/0.5/T2 formulas look up by Ref).
| Regenerating | Templates are generated by build.py – update settings there to add faculties/units, then re-run.
4. Key reference documents
| SR26 approach | 2026 Sustainability reporting approach & target status assessment framework – DRAFT Sep 2026
| SR25 documents | SR25 Reporting framework (Jan 2026); Faculty/portfolio engagement plan and comms 2025-26; 2025 end-year reporting master spreadsheet V0.2; Target status review process doc (Jan 2026); Target status assessment (final 18.3.26); SR25 Final (Word); SR25 Project close report and key lessons learnt
| Targets | Sustainability 2030 Updated Targets (Not for distribution) – Qual and Quan worksheets
5. Team processes
| Meetings | Weekly production meeting (SST + comms/design); standing items: progress, blockers/escalation, decisions.
| Communication | Direct messages for individual tasks; group channel for shared updates.

## P1 Project plan
↑ | 2026 Sustainability Report
P1. SR26 Project plan on a page
Project plan on a page
| Version control | DRAFT v0.16 – based on SR26 approach (Sep 2026)
| Context | The annual Sustainability Report is the University's core public account of sustainability progress. SR26 is a transition report following the refreshed Sustainability 2030 launch (~20 Oct 2026).
| Objectives / principles | Accurate and transparent (clear transition-year framing) • Fit-for-purpose (request only what is necessary, available and usable) • Evidence-led (each request linked to an indicator, report use and evidence) • Integrated (Databook is the primary quantitative source) • Reusable (templates and roles for 2027+) • Accessible (one web page per priority area: narrative + case studies) • Credible (independent review; traffic-light ratings deferred to 2027 reporting)
| Reporting model | Webpages by priority area; transition-year framing; no published traffic lights (internal ratings only); Databook for quantitative data; targeted qualitative requests; early case-study pipeline; Sustainability Reporting Review Group.
| Workstreams | Governance • Data collection & analysis (this workbook) • Content development • Communications & web build
| Key stakeholders | Director, Sustainability (decision owner) • COO • VCAG • University Executive • University Council • Investment Management Committee • Sustainability Reporting Review Group • Associate Deans Sustainability • Priority-area working groups • Central data owners (CI&S, CFOG, ESG, CIOG, MRE, AC&M, GCE, Education, SaSS, Indigenous, L&R) • Strategic Communications, digital & design • University Annual Report team
| Phases | Sep–Oct 2026 Set-up • Oct 2026 Process design & launch • Nov–Dec 2026 Evidence collection • Jan 2027 Drafting & validation • Feb–May 2027 Review & governance • May–Jun 2027 Publication & close-out
| Outputs | Requirements matrix • Request templates • Evidence register • Case-study pipeline • Draft report & issues paper • VCAG/UE/Council papers • Report website • Retrospective
| Success measures | Response rate • Reporting burden • Project effort • Data-quality issues • Web sessions, users and views • Stakeholder feedback
Key risks and controls
| Full-year implication | Report implies a full year of progress against targets launched 20 Oct → explicit transition-year framing.
| Onerous requests | Requests onerous or non-comparable → necessity and usability test; pilot templates; don't ask for data areas can't hold.
| Databook overlap | Databook and narrative requests overlap/conflict → one requirements matrix and evidence register; one source of truth per indicator.
| New working groups | Asked to evidence delivery before established → maturity-based 2026 request.
| Case studies dominate | → selection criteria: relevance, evidence, outcome, transferability, balance, permission.
| Late responses | → issue requirements early, support meetings, senior sponsorship, escalate gaps.
| Review group role | Unclear without traffic lights → approve review criteria and decision rights in advance.
| Annual Report divergence | → engage in October; shared dependency/data map; reconcile shared figures.
Decisions required (from SR26 approach)
| 1. Transition-year model | Director, Sustainability – Approved (internal traffic lights: sub-decision)
| 2. Evidence & engagement model | Director, Sustainability – Pending (awaiting Stefanus' WIP)
| 3. Assurance & governance pathway | Director, Sustainability – Closed
| 4. Modern slavery timeline alignment | Director, Sustainability (and Head of Procurement) – Open, watch item

## P2 Timeline & RASCI
↑ | 2026 Sustainability Report
P2. Timeline, RASCI & task register
Indicative dates from the SR26 approach – confirm governance dates with governance offices. Gantt bars fill automatically from Start/End.
[11 empty] | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug
| Phase / key activity | Key milestone | Start | End | R | A | S | C/I | Priority | Status | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02
Project set-up (Sep–Oct 2026)
| Confirm scope, reporting model, governance pathway and decisions | Decision log | 2026-09-14 | 2026-10-16 | SST | Director, Sustainability |  | VCAG (I) | High | Not yet started
| Project charter, schedule, RASCI, decision log, issues register | Approved by Oct | 2026-09-28 | 2026-10-23 | SST | Director, Sustainability |  | Comms, design | High | Not yet started
| Map refreshed targets/indicators to Databook, systems, owners | Requirements matrix | 2026-09-21 | 2026-10-16 | Stefanus | Gerard Healey | Rose | Data owners | High | Not yet started
| Confirm stakeholder structure (CGOP/CDEP/CDSS) and owners (Gerard: resilience, estate) | Stakeholder map | 2026-10-05 | 2026-10-16 | Stefanus | Gerard Healey |  |  | High | Not yet started
| Pilot request templates with 4 faculties (ABP, Arts, FBE, Science) | Pilot feedback | 2026-10-12 | 2026-10-30 | Stefanus | Gerard Healey |  | ADs Sustainability | High | Not yet started
| Approve Review Group criteria, decision rights, escalation pathway | Before collection | 2026-10-05 | 2026-10-30 | SST | Director, Sustainability |  | Review Group | Medium | Not yet started
Process design & launch (Oct 2026)
| Finalise templates and evidence register | Templates final | 2026-10-19 | 2026-10-30 | Stefanus | Gerard Healey |  |  | High | Not yet started
| Coordinate with University Annual Report team (dependency map) | Shared data map | 2026-10-05 | 2026-10-30 | SST | Director, Sustainability |  | Annual Report team | High | Not yet started
| Convene Strategic Comms, digital & design; agree comms RASCI | Kick-off | 2026-10-05 | 2026-10-23 | SST | Director, Sustainability | Strategic Comms | Design, digital | High | Not yet started
| Sustainability 2030 launch | ~20 Oct (TBC) | 2026-10-20 | 2026-10-20 |  |  |  |  | Milestone | Not yet started
| Brief contributor groups / working groups (after launch) |  | 2026-10-20 | 2026-11-06 | SST |  |  | Working groups | Medium | Not yet started
| Joint ADs Sustainability & ADs T&L session | Structured prompt in advance | 2026-10-19 | 2026-10-30 | SST |  |  | ADs | Medium | Not yet started
| Early engagement: socialise requirements in existing meetings (esp. education-related) | Stakeholder awareness | 2026-10-26 | 2026-10-30 | SST |  |  | Faculties, central units | High | Not yet started
Collection & evidence (Nov–Dec 2026)
| Collection launch: issue tailored requests (separate workbook per faculty/unit) | Requests formally issued | 2026-11-02 | 2026-11-06 | SST | Director, Sustainability | COO (sponsor) |  | High | Not yet started
| Collection period: stakeholders prepare responses and evidence | Initial submission | 2026-11-02 | 2026-12-15 | Faculties, central units |  | SST |  | High | Not yet started
| CDSS answers questions and records clarifications centrally | Clarifications log | 2026-11-02 | 2026-12-15 | CDSS |  |  |  | Medium | Not yet started
| Optional 1:1 meetings (on request) |  | 2026-11-02 | 2026-12-15 | SST |  |  | Data owners | Medium | Not yet started
| Responses and highlighted stories due | 15 Dec | 2026-12-15 | 2026-12-15 |  |  |  |  | Milestone | Not yet started
| First review: completeness and evidence quality | First QA assessment | 2026-12-14 | 2026-12-18 | SST |  |  |  | High | Not yet started
| Targeted follow-up where evidence is incomplete, ambiguous or missing (no second broad request; ask availability) | Resolved gaps | 2026-12-14 | 2026-12-24 | SST |  |  | Data owners | High | Not yet started
| Consolidation: finalise master, identify unresolved gaps, prepare drafting material | Consolidated master spreadsheet | 2026-12-21 | 2026-12-24 | SST | Director, Sustainability |  |  | High | Not yet started
Drafting & data validation (Jan 2027)
| Commence drafting from consolidated master |  | 2027-01-04 | 2027-02-05 | SST |  |  |  | High | Not yet started
| Confirm final quantitative figures (Databook) |  | 2027-01-04 | 2027-01-29 | SST |  | Data owners |  | High | Not yet started
| Review responses by indicator (A1 / T1 / T2) – no target status rating in 2026 |  | 2027-01-18 | 2027-02-05 | Rose (TBC) | Director, Sustainability | SST |  | High | Not yet started
| Full draft + issues paper; close evidence gaps |  | 2027-01-11 | 2027-02-05 | SST | Director, Sustainability |  |  | High | Not yet started
Review & governance (Feb–May 2027)
| VCAG papers due (Review Group findings) | 10 Feb | 2027-02-10 | 2027-02-10 | SST | Director, Sustainability |  |  | Milestone | Not yet started
| Sustainability Reporting Review Group | ~15 Feb (8–10 Feb TBC) | 2027-02-08 | 2027-02-15 | Rose (convenor, TBC) |  |  |  | Milestone | Not yet started
| VCAG – notes Review Group findings | 16 Feb | 2027-02-16 | 2027-02-16 |  |  |  |  | Milestone | Not yet started
| Investment Management Committee – Responsible Investments section | ~25 Feb (papers ~18 Feb) | 2027-02-18 | 2027-02-25 | SST |  |  |  | Milestone | Not yet started
| Full-report finalisation; Strategic Comms review; reconcile Annual Report data |  | 2027-02-16 | 2027-02-26 | SST |  | Strategic Comms |  | High | Not yet started
| VCAG – notes full report | ~2 Mar (papers ~25 Feb) | 2027-03-02 | 2027-03-02 |  |  |  |  | Milestone | Not yet started
| University Executive – notes report | ~25 Mar (papers ~12 Mar) | 2027-03-25 | 2027-03-25 |  |  |  |  | Milestone | Not yet started
| University Council – approves report | ~6 May (papers ~10 Apr) | 2027-05-06 | 2027-05-06 |  |  |  |  | Milestone | Not yet started
Publication & close-out (May–Jun 2027)
| Web build; QA, accessibility and web checks; agree analytics measures | Before launch | 2027-03-01 | 2027-05-28 | Comms/digital |  | SST |  | High | Not yet started
| Publish report (year-specific URL + landing page) | June | 2027-06-01 | 2027-06-30 | Comms/digital | Director, Sustainability |  |  | Milestone | Not yet started
| Monitor engagement; project retrospective; improvements for 2027 cycle |  | 2027-06-01 | 2027-07-30 | SST |  | Comms, design |  | Medium | Not yet started

## P3 To do – comms+web
↑ | 2026 Sustainability Report
P3. Comms + web build to-do list
Track comms, web build and design tasks. Priority: Low / Medium / High / Urgent.
| Report component or page | Case study/content name | Lead | Priority level | Agreed deadline | Action needed | Details | Complete? (Y/N) | Updates/blockers/FYI
| Web – whole report | Year-specific report URL | Comms/digital | High |  | Set up | Use a year-specific URL (e.g. /sustainabilityreport/2026) and retain the central reports landing page (SR25 lesson).
| Web – whole report | Analytics measures | Comms/digital | High |  | Agree before launch | Agree web sessions, users and views measures before launch so project close can report them.
| Web – whole report | Accessibility & reviewer workflow testing | Comms/digital | High |  | Test | Navigation, links, mobile usability, accessibility, reviewer workflows – before governance approval.
| Report introduction | Transition-year framing | SST | High |  | Draft | Explain former SP2030 vs Sustainability 2030 (launched ~20 Oct 2026).
| Whole report | Whole-report review | Strategic Comms | High |  | Schedule | Schedule early enough for material changes.

## P4 Content checklist
↑ | 2026 Sustainability Report
P4. Content contributor checklist
Stakeholder management for report content: review by contributors, images, credits and captions, post-launch follow-up.
| Report section | Case study | Activity areas | Review required? (Y/N) | Content contributors | Project team liaison | Sent for review (date) | Changes required? (Y/N) | SR26 draft updated? (Y/N) | SR26 website updated? (Y/N) | Images shared? (Y/N) | Image URL | Known image gap | Credit noted? | Caption text | Permission to publish confirmed? | Post-launch: send to | CC | Sent (date) | Complete? (Y/N)

## P5 SR26 page index
↑ | 2026 Sustainability Report
P5. SR26 page index (URLs)
| Ref | Sustainability 2030 component | Page name | Story / case study | SR26 link | Page description | Character count | SR25 equivalent page
| FM01 | N/A | Landing page
| FM02 | N/A | Overview (transition year)
| FM03 | N/A | Our impact
| PA01 | Education and research | Exceptional education
| PA02 | Education and research | Transformational research
| PA03 | Sustainability leadership | Climate leadership
| PA04 | Sustainability leadership | Nature and biodiversity
| PA05 | Sustainability leadership | Responsible AI
| PA06 | Resilient University | Estate and infrastructure
| PA07 | Resilient University | Circular economy
| PA08 | Resilient University | Responsible procurement
| PA09 | Resilient University | Modern slavery and human rights
| PA10 | Resilient University | Responsible investments
| PA11 | Enablers | Enablers

## Lists (hidden)
(not used – no target status rating in 2026) | Data owner confirms | Request status | Y/N | Report section
Please select from dropdown | Yes | Not sent | Yes | Report introduction
| No | Sent | No | Our impact
| Partially – see comments | 1:1 meeting | TBC | Exceptional education
|  | Received |  | Transformational research
|  | First review |  | Climate leadership
|  | Follow-up |  | Nature and biodiversity
|  | Complete |  | Responsible AI
|  | Not required |  | Estate and infrastructure
Circular economy
Responsible procurement
Modern slavery and human rights
Responsible investments
Enablers